## Sheet1
Task Number | Task Name | Duration (days) | Dependency | Status
1 | Analysis and Requirement Gathering
1.1 | Brainstorming Ide | 6 |  | done
1.2 | Review Business case dan Project Vision | 6 | 1.1 | done
1.3 | Create Product Backlog | 6 | 1.2 | done
1.4 | Membuat user stories | 6 | 1.3 | done
1.5 | Buat task,Estimasi dan Sprint backlog | 6 | 1.4 | done
2 | Sprint 1
2.1 | Membuat class diagram | 3 | 1.4
2.2 | Develop Authentication | 3 | 2.1
2.3 | Develop fitur Home | 12 | 2.2
2.4 | Develop fitur profil | 12 | 2.2
2.5 | Testing fitur sprint 1 | 2 | 2.3, 2.4
2.6 | Penggabungan fitur sprint 1 | 3 | 2.5
3 | Sprint 2
3.1 | Update task | 3 | 2.6
3.2 | Develop fitur Food Calories | 12 | 3.1
3.3 | Develop fitur Food Recomendation | 12 | 3.1
3.4 | Testing fitur sprint 2 | 3 | 3.2, 3.3
3.5 | Penggabungan fitur sprint 2 | 5 | 3.4
4 | Sprint 3
4.1 | Sprint review, evaluation | 2 | 3.5
4.2 | Develop fitur Reminder | 14 | 4.1
4.3 | Develop fitur Week Evaluation, Share | 14 | 4.1
4.4 | Testing fitur 3 | 2 | 4.2, 4.3
4.5 | Review, penggabungan, debugging | 11 | 4.4