## PPL
At Risk | Task Name | Start Date | End Date | Duration | % Complete | Predecessors | Comments
| Analysis and Requirement | 2016-02-09 | 2016-03-14 | 25d | 20%
| Brainstorming Ide | 2016-02-09 | 2016-02-15 | 5d | 50%
TRUE | Pembuatan Business case dan Project Vision | 2016-02-09 | 2016-02-15 | 5d | 50%
| Pembuatan Product Backlog | 2016-02-16 | 2016-02-22 | 5d | 0% | 4
| Membuat user stories | 2016-03-01 | 2016-03-07 | 5d
| Buat task,Estimasi, Software Model, dan Sprint backlog | 2016-03-08 | 2016-03-14 | 5d
| Sprint 1 | 2016-03-15 | 2016-04-11 | 20d
| Update Task | 2016-03-15 | 2016-03-18 | 4d
| Develop fitur profile | 2016-03-19 | 2016-03-22 | 3d
| Develop fitur schedule | 2016-03-23 | 2016-04-04 | 9d |  | 10; 5
| Develop fitur reminder | 2016-03-23 | 2016-04-04 | 9d
| Testing fitur sprint1 | 2016-04-05 | 2016-04-07 | 3d
| Penggabungan fitur pada sprint1 | 2016-04-08 | 2016-04-11 | 2d
| Sprint 2 | 2016-04-12 | 2016-05-09 | 20d
| Sprint Review, Evaluation, & Update Task | 2016-04-12 | 2016-04-15 | 4d
| Develop fitur food calories | 2016-04-17 | 2016-04-29 | 11d
| Develop fitur home | 2016-04-17 | 2016-04-29 | 11d
| Testing fitur Sprint 2 | 2016-04-30 | 2016-05-03 | 3d
| Penggabungan fitur pada sprint2 | 2016-05-04 | 2016-05-09 | 4d
| Sprint 3 | 2016-05-10 | 2016-06-10 | 24d
| Sprint Review, Evaluation, & Update Task | 2016-05-10 | 2016-05-12 | 3d
| Develop fitur week evaluation | 2016-05-13 | 2016-05-27 | 11d
| Develop fitur food recommendation | 2016-05-13 | 2016-05-27 | 11d
| Testing fitur sprint 3 | 2016-05-28 | 2016-05-30 | 2d
| Review, penggabungan, debuging | 2016-05-31 | 2016-06-10 | 9d

## Discussions
Row 4 | Discussion Title | Sub-task 2 | Jenny Gruening | 27/06/13 9:02
| Comments | You can add discussions, notes, or emails to discussions. | Jenny Gruening | 27/06/13 9:02